## Trang tính1
Category | Task Name | Duration (days) | Start | Finish | Assignees | Done | Notes
Phase | INCEPTION | 37 | 2024-03-28 | 2024-05-04 |  | TRUE
Iteration | I0 - Setup | 9 | 2024-03-28 | 2024-04-06 |  | TRUE
Task | Group registration |  | 2024-03-28 | 2024-03-28 | Trọng Phúc | TRUE
Task | Set up Workspace: Slack, Jira, Github, Gdrive | 1 | 2024-04-02 | 2024-04-03 | Ngọc Châm | TRUE
Meeting | First Meeting |  | 2024-04-04 | 2024-04-04 | All | TRUE
Task | Answer PA0 requirements, write the project description | 2 |  | 2024-04-06 | Minh Triết | TRUE
Meeting | Sprint 1 Planning meeting |  | 2024-04-06 | 2024-04-06 | All | TRUE
Milestone | Submit the Project Proposal - PA0 |  |  |  | Ngọc Châm | TRUE
Iteration | I1 - Project Definition | 14 | 2024-04-06 | 2024-04-20 |  | TRUE
Meeting | Sprint1 Weekly Scrum meeting 1 |  | 2024-04-08 | 2024-04-08 | All | TRUE
Task | Initiate planning phase by trying to fill the Software Development Plan PA1.a | 7 | 2024-04-08 | 2024-04-15 | Minh Triết + Tấn Phát | TRUE
Task | Plan the initial schedules and objectives for the upcoming five sprints |  |  |  | Ngọc Châm | TRUE
Task | Prepare an initial version of the Vision Document - PA1.b | 4 | 2024-04-11 | 2024-04-16 | Trọng Phúc + Trường Sinh | TRUE
Meeting | Sprint1-Weekly Scrum meeting 2 |  | 2024-04-12 | 2024-04-12 | All | TRUE
Task | Update weekly scrum meeting notes PA1.c | 1 | 2024-04-12 | 2024-04-13 | Minh Triết | TRUE
Meeting | Sprint1 Review Sprint meeting |  | 2024-04-16 | 2024-04-16 | All | TRUE
Meeting | Sprint1 Planning Next Sprint meeting |  | 2024-04-18 | 2024-04-18 | All | TRUE
Milestone | Submit PA1 |  | 2024-04-20 | 2024-04-20 | Ngọc Châm | TRUE
Iteration | I2 - Requirement Demonstration | 14 | 2024-04-20 | 2024-05-04 |  | TRUE
Task | Revised project plan - PA2.a |  | 2024-04-20 | 2024-04-20 | Ngọc Châm | TRUE
Task | Detailed vision document PA2.b |  |  |  | Tấn Phát | TRUE
Task | Update weekly scrum meeting notes | 1 | 2024-04-20 | 2024-04-21 | Trọng Phúc | TRUE
Task | Use-case model PA2.c | 8 | 2024-04-21 | 2024-04-29 | Minh Triết | TRUE
Task | Use-case specification PA2.d | 8 |  |  | Trọng Phúc | TRUE
Meeting | Sprint2 - Weekly Scrum meeting 1 |  | 2024-04-24 | 2024-04-24 | Minh triết | TRUE
Task | Review and finish | 1 | 2024-04-28 | 2024-04-29 | All | TRUE
Task | Update weekly scrum meeting notes PA2 | 1 |  |  | Trường Sinh | TRUE
Meeting | Sprint2 - Review Sprint meeting |  | 2024-04-29 |  | All | TRUE
Meeting | Sprint2 - Weekly Scrum meeting 2 |  | 2024-05-02 | 2024-05-02 | All | TRUE
Meeting | Sprint2 - Planning Next Sprint meeting |  | 2024-05-04 | 2024-05-04 | Minh triết | TRUE
Milestone | Submit PA2 |  | 2024-05-04 | 2024-05-04 | Ngọc Châm | TRUE
Phase | ELABORATION | 20 | 2024-05-05 | 2024-05-25 |  | TRUE
Iteration | E1 Architectural Definition | 13 | 2024-05-05 | 2024-05-18 |  | TRUE
Meeting | Sprint3 Weekly Scrum meeting 1 |  | 2024-05-05 | 2024-05-05 | All | TRUE
Task | Use-case specification - 2nd submission | 5 |  | 2024-05-10 | Ngọc Châm + Trọng Phúc | TRUE
Task | Define software architecture | 5 |  |  | Minh Triết + Tấn Phát + Trọng Phúc | TRUE
Task | Model class diagrams for each of the key components defined in the architecture | 5 | 2024-05-10 | 2024-05-15 | Minh Triết + Trường Sinh | TRUE
Task | Review and finish |  | 2024-05-15 | 2024-05-15 | All | TRUE
Task | Update weekly scrum meeting notes PA3.d |  |  |  | Ngọc Châm | TRUE
Meeting | Sprint3 - Review Sprint meeting |  | 2024-05-15 | 2024-05-15 | All | TRUE
Meeting | Sprint3 - Planning Next Sprint meeting |  | 2024-05-17 | 2024-05-17 | All | TRUE
Milestone | Submit PA3 |  | 2024-05-18 | 2024-05-18 | Ngọc Châm | TRUE
Iteration | E2 User Interface Design | 7 | 2024-05-18 | 2024-05-25 |  | TRUE
Task | Revise SAD | 4 | 2024-05-18 | 2024-05-22 | Minh Triết + Tấn Phát + Trường Sinh | TRUE
Task | UI prototype | 4 |  |  | Trọng Phúc + Ngọc Châm | TRUE
Meeting | Sprint4 Weekly Scrum meeting 1 |  | 2024-05-22 | 2024-05-22 | All | TRUE
Task | Update weekly scrum meeting notes PA4.c |  |  |  | Ngọc Châm | TRUE
Task | Review and finish | 1 | 2024-05-22 | 2024-05-23 | All | TRUE
Meeting | Sprint4 Review Sprint meeting |  | 2024-05-24 | 2024-05-24 | All | TRUE
Meeting | Sprint4-Planning Next Sprint meeting |  | 2024-05-24 | 2024-05-24 | All | TRUE
Milestone | Submit PA4 |  | 2024-05-25 | 2024-05-25 | Ngọc Châm | TRUE
Phase | CONSTRUCTION | 17 | 2024-05-25 | 2024-06-11 |  | TRUE
Task | Implement all key features | 11 | 2024-05-25 | 2024-06-05 | All | TRUE
Meeting | Sprint5 Weekly Scrum meeting 1 |  | 2024-05-29 | 2024-05-29 | All | TRUE
Task | Test plan | 2 | 2024-05-30 | 2024-06-01 | Tấn Phát + Minh Triết | TRUE
Task | Test cases | 4 | 2024-06-01 | 2024-06-05 | Trọng Phúc + Trường Sinh | TRUE
Meeting | Sprint5 Weekly Scrum meeting 2 |  | 2024-06-06 | 2024-06-06 | All | TRUE
Task | Update weekly scrum meeting notes PAS.c |  |  |  | Ngọc Châm | TRUE
Task | Test case execution | 3 | 2024-06-07 | 2024-06-10 | Trọng Phúc + Trường Sinh | TRUE
Task | Test report | 3 |  |  | Ngọc Châm | TRUE
Task | Slide for representation | 2 | 2024-06-09 | 2024-06-11 | All | TRUE
Meeting | Sprint5 Review Sprint meeting |  | 2024-06-10 | 2024-06-10 | All | TRUE
Task | Update weekly scrum meeting notes |  |  |  | Minh Triết | TRUE
Milestone | Submit PA5 |  | 2024-06-11 | 2024-06-11 | Ngọc Châm | TRUE